## Project Status Dashboard
PROJECT STATUS REPORT DASHBOARD
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
Customer Segmentation Using RFM Analysis |  |  |  | 24/7/23 | In Progress | 90.9%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | CATEGORY | REMARKS / PROBLEMS ENCOUNTERED Likhit | REMARKS / PROBLEMS ENCOUNTERED Kunnithi
CRM Workshop | BA | 2023-06-08 | 2023-06-08 | 1 | Complete | Initiate
Understanding concepts of RFM Analysis and implementation using Python and Power BI | BA | 2023-06-12 | 2023-06-16 | 5 | Complete | Initiate
Interview user to gather requirements to estimate timeline | BA | 2023-06-13 | 2023-06-13 | 1 | Complete | User Requirement
Document business requirements | BA | 2023-06-13 | 2023-06-14 | 2 | Complete | User Requirement
Function List | BA | 2023-06-16 | 2023-06-16 | 1 | Complete | User Requirement
Function Spec. | BA | 2023-06-16 | 2023-06-23 | 8 | Complete | User Requirement
Business Rule | BA | 2023-06-26 | 2023-06-26 | 1 | Complete | User Requirement
Create Workflow | BA | 2023-06-23 | 2023-06-26 | 4 | Complete | User Requirement
BSR | BA | 2023-06-26 | 2023-06-26 | 1 | Complete | User Requirement
Review Workflow​ | BA | 2023-06-27 | 2023-06-27 | 1 | Complete | User Requirement
Present Project Agenda | BA | 2023-06-28 | 2023-06-28 | 1 | Complete | User Requirement
Data Cleaning And Data Preparation | BA | 2023-07-03 | 2023-07-06 | 4 | Complete | Development | Created new SQL scripts to clean data (removing null and non-customer transactions and set range of data
Transform Data | BA | 2023-07-07 | 2023-07-07 | 1 | Complete | Development | 1. Generate new tables to create new fields for performing analysis e.g. user's favourite brand ranking 2. Considering whether if the RFM analysis by brand should be calculated based on each member's favourite brand only or calculate based on brands that member bought at least once
Recency, Frequency, and Monetary Calculation | BA | 2023-07-10 | 2023-07-10 | 1 | Complete | Development
RFM Analysis and Segmentation | BA | 2023-07-11 | 2023-07-17 | 7 | Complete | Development | 1. Removed time slicer in every page of the report due to techinical capability and performance isssues. 2. Replaced the third page of the report with RFM segment comparison of June 2021-2022 and June 2022-2023 because the comparison shows more valuable insights. 3. Changed cutoff percentile to be more accurate for each values | 1. Generate graph that used for filter out outliner including scatter charts of flagmentation of customer baase on rfm value, bar charts of density of customer in percentile range, 3d scatter of flagmentation, 3d of centroid of each segmentation, line charts of trend of amount of customer from 0 to target percentile. Create some graph of overview of rfm report 2. integrate the SQL and python code to be able to use in with likhit' SQL and adjust the code to use same data and cutoff percentiles.
Segment into brand-level groups | BA | 2023-07-18 | 2023-07-20 | 3 | Complete | Development | Fixed bugs: error when importing csv file from SQL to Power BI, unequal number of customers in each imported tables
Data Dictionary | BA | 2023-07-21 | 2023-07-21 | 1 | Complete | Development
Create test case | BA | 2023-07-24 | 2023-07-24 | 1 | Complete | Testing
Review test case | BA | 2023-07-25 | 2023-07-25 | 1 | Complete | Testing
UAT Testing | BA | 2023-07-26 | 2023-07-27 | 2 | Complete | Testing
Document UAT sign off | BA | 2023-07-28 | 2023-08-01 | 5 | Not Started | Implementation
Transfer Knowledge | BA | 2023-08-02 | 2023-08-04 | 3 | Not Started | Implementation
TASK STATUS % | automatically populates
STATUS | COUNT | %
Not Started | 2 | 9.091%
In Progress | 0 | 0%
Complete | 20 | 90.91%
Overdue | 0 | 0%
On Hold | 0 | 0%
TOTAL | 22 | 100%
TASK CATEGORY % | automatically populates |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
Initiate | 2 | 10.53% |  | Actions | 0
User Requirement | 9 | 47.37% |  | Change Requests | 0
Development | 6 | 31.58%
Implementation | 2 | 10.53%
TOTAL | 19 | 100%